## Gantt Chart
	SWE 573 – Software Development Practice				6%
	Bogazici University
	Hüseyin DEMİR		Pazar 6.Aralık.2020

										51					52					53					01					02					03					04					05					06					07					08					09					10					11					12					13					14					15					16					17					18					19					20					21					22					23
WBS	Task Names	Resource Names	Start	Duration	Finish	% Complete	Calendar days	Days Completed	Days Remaining	Ara-20					Oca-21					Şub-21					Mar-21					Nis-21					May-21					Haz-21
			10-Ara-2020	6	17-Ara-2020	6%	8			10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08
	Requirements	Project Infra Reqs	10-Ara-2020	3	14-Ara-2020	20%	5	0	6
	Twitter Developer Account
	Twitter Developer Account		10-Ara-2020	1	10-Ara-2020	20%	1	0	1
	Infrastructure Setup
	Database Environment Construction		10-Ara-2020	2	11-Ara-2020	0%	2	0	2
	Application Environment Construction		12-Ara-2020	2	14-Ara-2020	0%	3	0	2
	Git Integration for Project		13-Ara-2020	1	13-Ara-2020	0%	1	0	1
	Frontend Setup
	Login Page Implementation		15-Ara-2020	2	16-Ara-2020	0%	2	0	2
	Home Page Implementation		16-Ara-2020	2	17-Ara-2020	0%	2	0	2
	Stats Page Impelementation		17-Ara-2020	1	17-Ara-2020	0%	1	0	1

	Implementation